## duration-1
area | duration | Main tasks | Data requirement | Deliverable
>1 ha | 2-3 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
1-5 ha | 3-4 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
6-10 ha | 4-6 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
11-20 ha | 6-8weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
21-30 ha | 9-12 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
31-50ha | 3-4 months | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
51-75 ha | 4-6 months | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
75-100 ha | 6-9 months | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
>100 ha | Minimum 9 months | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)

## duration-2
area | duration | Main tasks | Data requirement | Deliverable
>1ha | 2-3 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
1-5 ha | 3-6 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
6-10 ha | 6-9 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
11-20 ha | 2-3 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
21-30 ha | 3-4 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
31-50ha | 4-6 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
51-75 ha | 6-9 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
75-100 ha | 9-12 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
>100 ha | Minimum 1 year | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network

## duration-3
area | duration | Main tasks | Data requirement | Deliverable
>1ha | 3-4 weeks | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
1-5 ha | 4-8 weeks | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
6-10 ha | 8-12 weeks | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
11-20 ha | 3-4 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
21-30 ha | 4-5 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
31-50ha | 5-7 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
51-75 ha | 7-10 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
75-100 ha | 10-12 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
>100 ha | Minimum 1 year | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
|  | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)